## Checklist
Asana Sprint Tracking: Backlogs, Capacity, and Reports
Saskia Linwood, Senior Editor · 28.02.2026
✓ | Step | Section
☐ | Create the Backlog project — priority-ordered list view; add sections for Ready, Refined, Triaged | Sprint Tracking Setup in Asana
☐ | Create the Sprint project — board view with Backlog, In Progress, In Review, Done columns | Sprint Tracking Setup in Asana
☐ | Add custom fields — Story points (number), Priority (single-select), Type (single-select), Status (single-select) | Sprint Tracking Setup in Asana
☐ | Pick the sprint duration — 1–3 weeks; 2 weeks is the modal choice for cross-functional teams | Sprint Tracking Setup in Asana
☐ | Save the Sprint project as a template after the first iteration; clone it for each new sprint | Sprint Tracking Setup in Asana
☐ | Workload inputs — Story points custom field, per-person capacity (e.g. 8 points per 2-week sprint) | Planning Sprint Capacity
☐ | Estimates — relative (Fibonacci) is more honest than absolute; absolute (hours) creates false precision | Planning Sprint Capacity
☐ | Assignee balance — Workload view (Advanced) shows everyone\'s sum at a glance | Planning Sprint Capacity
☐ | Spillover — incomplete tasks at sprint end auto-roll if the rule is set; otherwise the team decides per task | Planning Sprint Capacity
☐ | Buffer — leave 20% of capacity unallocated for emergencies, interruptions, support work | Planning Sprint Capacity
☐ | Daily standup — walk the board right-to-left (Done → In Review → In Progress → Backlog); surface blockers first | Tracking Sprint Execution
☐ | Blocked items — Blocked custom field; sort or filter to find them fast; assign an unblocker as part of the standup | Tracking Sprint Execution
☐ | Owner updates — keep updates in task comments, not in chat; chat fragments context | Tracking Sprint Execution
☐ | Automation — when section = In Review, assign to lead reviewer; when section = Done, notify QA | Tracking Sprint Execution
☐ | Recurring routines — sprint kickoff task, mid-sprint check, retro task — all as recurring or templated | Tracking Sprint Execution
☐ | Sprint progress dashboard — burnup of completed points, count of in-progress vs completed, blocker count | Sprint Reports and Retrospectives
☐ | Closed sprint review — total points completed, spillover count, blockers resolved, blockers persisting | Sprint Reports and Retrospectives
☐ | Retrospective questions — what worked, what didn\'t, what to try next; 30–45 minutes max | Sprint Reports and Retrospectives
☐ | Action items — retro outcomes become tasks in the next sprint; track completion to make retros stick | Sprint Reports and Retrospectives
☐ | Velocity tracking — store closed-points-per-sprint in a separate Goals page or spreadsheet for trend | Sprint Reports and Retrospectives
☐ | Missing native burndown — workaround exists; takes manual upkeep | Limitations Versus Jira or Linear
☐ | Story points as second-class data — workable, but Jira treats them natively | Limitations Versus Jira or Linear
☐ | Git event automation — Linear is best-in-class; Jira is solid; Asana has integrations but they\'re lighter | Limitations Versus Jira or Linear
☐ | Advanced sprint reports — cumulative flow, cycle time, lead time — minimal in Asana; deep in Jira | Limitations Versus Jira or Linear
☐ | Integrations that close the gap — Linear or Jira sync, Everhour for time, third-party burndown apps | Limitations Versus Jira or Linear
Full article: https://asanatracker.com/asana-sprint-tracker
AsanaTracker may earn a commission when readers sign up to Asana through links on this site. Editorial decisions stay independent.